## Task Tracker
City of Aiken Economic Development Actions (12/8/21)
AMDC Priorities
Goal 3-Targeted Residential and Business Development: The AMDC will create new opportunities for commercial and residential development through partnerships and existing groups, as well as new investors, to increase the quality and density of those living and working within the City of Aiken.
TASK | DESCRIPTION | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS | ASSESSMENT
Provide a range of housing types at diverse price points | Work with community stakeholders to identify target areas for residential development/redevelopment within their communities, with the downtown area of Aiken being one area of focus | Aiken Municipal Development Commission (AMDC), City of Aiken, Neighborhood Associations/Other Community Organizations | The AMDC created a committee to explore opportunities to target potential areas for redevelopment/investment. Additionally, the AMDC has actively pursued redevelopment for identified areas in downtown Aiken, with Project Pascalis representing a significant portion of time and work. | The 'Targetting' Committee has recommended several action steps related to identifying prospective parcels for consideration as attractive development sites. Additionally, the AMDC has assisted the City in the development of possible projects to be financed with Plutonium Settlement funds (to be allocated in 2022 as well as COVID Relief-related funds, to be allocated in Fall 2021.
| Work with other development organizations such as the Aiken Corporation and local CDCs to coordinate the acquisition and assembly of land and/or derelict properties, to be repackaged as available sites for medium-density housing/mixed-use, mixed-income residential and marketed to the development community where appropriate | AMDC, City of Aiken, Local CDCs | 1)The Commission has toured DuPont Landing, an affordable housing and mixed-use development led by an arm of Second Baptist Church with considerable success. 2)The AMDC has initiated conversations with the Aiken Housing Authority concerning future plans for the Hahn Village property, and members have met with the Board of Directors of that organization to explore options. 3)Included in Plutonium Settlement funding requests are projects related to Aiken's Northside and the York Street connector to I-20. | Committee members are gathering information about parcels possibly available within the 'Parkway District' for residential or commercial development.
| Continue to work with local community development organizations (i.e. Second Baptist CDC) to coordinate targeted infill redevelopment of vacant/derelict properties | AMDC, Local CDCs, Neighborhood Associations/Other Community Organizations |  | (See Above)
| Work to revise current zoning ordinance to re-zone properties low-density single-family residential properties for additional medium-density residential development, where appropriate | City of Aiken | MCL 12/21: Planning staff work continuously with area stakeholders to navigate the rezoning process. The Planning Commission and City Council hear and act upon many rezoning applications for a variety of uses every year. | The Commission is prepared to seek assistance from the City as opportunities requiring this response are identified. City of Aiken staff responds that they are always amenable to meeting with AMDC and other community stakeholders about possible rezoning applications, which are reviewed by the Planning Commission and City Council for ultimate decision by City Council. City Council may also direct that the Planning Commission study such a topic.If the AMDC has specific areas in mind for rezoning, Planning Staff can meet with them to discuss applicable sections of the Zoning Ordinance that should be considered in any decision to rezone. The AMDC may then wish to lead outreach with property owners regarding the benefits of rezoning their properties.
| Issue RFPs for land assembled for housing development/redevelopment to the development community; ensure community and local stakeholder involvement throughout the process | AMDC, City of Aiken |  | The Commission will use this mechanism when appropriate, such as in advancing development of the former Jackson Petroleum site at Richland Avenue and Williamsburg Street when it is fully remediated.
Incentivize medium-to-high density residential mixed-use development downtown | Work with the Aiken Municipal Development Commission, local business leaders, and other City economic development stakeholders to increasing awareness of available incentives for downtown development/redevelopment | City of Aiken, AMDC, Aiken Downtown Development Association | The AMDC created a committee to study and advise on the best policies and practices to enhance the City's ability to serve the needs of businesses, developers, and investors in our community while addressing regulatory, governance, and planning requirements | (See Goal 4 below)
| Engage community stakeholders in creating a broader vision for a live/work/play, 18-to-24-hour downtown; use this vision to guide future development in downtown | City of Aiken, AMDC, Aiken Downtown Development Association | (See comparable narrative under City Priorities below.)
| Explore options for more flexible zoning and/or special districts (including special taxing districts such as TIFs) to encourage higher-density, mixed-used/mixed income development, and options for incentivizing affordable housing, including density bonuses, tax credits/incentives, public service enhancements, etc. Again, ensure that any changes made are appropriately communicated to the broader development community | City of Aiken, AMDC, Aiken Downtown Development Association |  | The Commission is prepared to seek assistance from the City as opportunities requiring this response are identified.
Engage in partnerships to assemble land/properties for redevelopment in target growth areas | Explore options for property acquisition by the City/Aiken Municipal Development Commission of parcels that can be acquired, assembled, and developed for medium-to-high-density mixed-use, mixed-income residential development | City of Aiken, AMDC | The AMDC created a committee to explore opportunities to target potential areas for redevelopment/investment. Additionally, the AMDC has actively pursued redevelopment for identified areas in downtown Aiken, with Project Pascalis representing a significant portion of time and work.
Leverage new Steeplechase site | Leverage the attention/publicity Aiken is receiving for the new Steeplechase Site into a broader discussion about the future of the equine industry in Aiken; explore options for ancillary development to the site designed to serve racegoers, horse owners/breeders, and other stakeholders. | City of Aiken, AMDC, Aiken Steeplechase Association |  | Contact has been made with Steeplechase leaders and will continue in 2022 to pursue these objectives.
Explore other opportunities for new Steeplechase site utilization year-round, including camps, training, and other uses that would keep the site active and well-utilized during the off-season.
| Explore other opportunities for new Steeplechase site utilization year-round, including camps, training, and other uses that would keep the site active and well-utilized during the off-season. | City of Aiken, AMDC, Aiken Steeplechase Association |  | Contact has been made with Steeplechase leaders and will continue in 2022 to pursue these objectives.
Develop Hotel Aiken site | Conduct market study to confirm optimal development plan for the hotel building and parcel with/without) adjacent parcels. Consider residential housing on upper floors of hotel; parking on adjacent sites as part of any new construction. Bar / restaurant / entertainment as part of the development. | City of Aiken, Downtown Development Association, AMDC | Property has been purchased and a conversations are being held with a prospective development group for action in 2022. | This project, among others in under active consideration by the AMDC.
Assess current and potential market conditions and projections for retail, restaurants / bars, residential, hotel. This will further inform the optimal plan for the Hotel Aiken building and parcel.
Explore development potential of Old County Hospital site | Enhance west entrance of Aiken with potential townhome / small village type development. Link development via multimodal paths to the Lessie B. Price Community Center and Eustis Park Playground | City of Aiken, AMDC | This property is owned by Aiken County Government and is under option at the current time. | This project, among others in under active consideration by the AMDC.
Assess development opportunities on East Richland Ave | Identify derelict, underdeveloped or inactive sites; combine with gateway enhancements to invigorate entrances and exits | City of Aiken | The AMDC created a committee to explore opportunities to target potential areas for redevelopment/investment. Additionally, the AMDC has actively pursued redevelopment for identified areas in downtown Aiken, with Project Pascalis representing a significant portion of time and work.
Develop amenities/services for Citizens Park | Identify 10-12 acres in or adjacent to Citizens Park for development of a hotel and restaurant for families and athletes attending tournaments and games at Citizens Park. | City of Aiken, AMDC | TH: To be considered in the coming year. MCL 12/21: Expansion of Citizen Park amenities remains a priority for Council, who, with City staff, continue to consider development options based on available funding.
Goal 1- Aiken Innovation and Impact District: The AMDC will spearhead the development of an Innovation and Impact district to capitalize upon imminent investments being made on and near the campus of the university of South Carolina Aiken such as the Advanced Manufacturing Center and the South Carolina National Guard DreampPort. These projects are expected to be in operation within the next 2-3 years, and it is imperative that efforts to secure land, establish partnerships, anticipate policy changes necessary for this venture's success, and planning for appropriate amenities to support a living/working environment to attract and retain a world-class collection of businesses, investors and employees.
TASK | DESCRIPTION | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS | ASSESSMENT
Establish an Innovation District near USC Aiken | Examine opportunities to establish a special district close to USC Aiken, such as the WestEdge Innovation District in Charleston, to foster clustering of businesses linked to advanced manufacturing, software/IT and technology, and take advantage of existing synergies in the region. The district should be mixed-use in nature, providing access to retail, dining, housing, and other amenities, in support of new research and production facilities operated by the private sector/universities | City of Aiken, AMDC, Aiken Chamber, EDP | The AMDC created a committee to study and advise on the best practices from other communities with similar facilities and to explore options for encouraging and/or leading in the pursuit of this project. They are currently engaged in the following activities: • Socializing the idea with various entities that could become partners. • Beginning the process of studying successful established innovation districts and imagining what they may look like in the future. • Planning to become more aggressive when construction of the AMC begins. • Lobbying to attracting the $20M Collaboration Center proposed by the Universities that are part of the Battelle contract for SRSL to potentially be the cornerstone of the innovation district.
Identify location(s) at or adjacent to USC Aiken and develop master plan for an innovation center associated with the AMC and DreamPort | Build on momentum created by investments in cybersecurity and advanced manufacturing to further catalyze investment and development of innovation economy. | City of Aiken, AMDC, Chamber of Commerce, USC Aiken | (See above narrative)
Goal 5-Marketing Aiken as a Good Community for Investment : The AMDC will initiate marketing activities in support of broader recognition of Aiken as an attractive location for business.
TASK | DESCRIPTION | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS | ASSESSMENT
Marketing Aiken as a Great Place to Do Business | Review existing marketing efforts and establish new ones as necessary to focus upon attracting prospective new investors and developers to our community | AMDC, City of Aiken | The AMDC created a committee to explore the best ways to incorporate promoting the attractiveness of Aiken as a viable option for investment and economic development. | The group has met with City officials to study existing marketing efforts (tourism, recreation, the City's website, etc.) and to encourage the use of these tools to also publicize exciting developments in our city to a wider audience of prospects.
Goal 4- Making Aiken More "Business Friendly": The AMDC will work with City officials to reaffirm that necessary regulatory and approval processes are clear, grounded in defined purposes, and fair.
TASK | DESCRIPTION | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS | ASSESSMENT
Actively pursue, in partnership with the City, the development and implementation of regulatory and permitting practices that are as 'business friendly' as possible | Review existing practices and seek to reduce or eliminate burdensome or time-consuming requirements not required by law or regulation or which might be accomplished in other ways. | AMDC, City of Aiken | The AMDC created a committee to study and advise on the best policies and practices to enhance the City's ability to serve the needs of businesses, developers, and investors in our community while addressing regulatory, governance, and planning requirements. City officals have been working on this priority as well, and revisions in ordinances and practices are emerging for Council action and staff implementation. | Communication will continue on 2022.
Goal 2-Whiskey Road Corridor/Development Ramifications of Transportation Improvements: The AMDC will support efforts by the City and County to implement existing plans for significant improvements to traffic flow, safety, and increased economic development.
TASK | DESCRIPTION | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS | ASSESSMENT
Invest in enhancement and improvements to Gateways and parkways | 1) Confirm key entrance and exits to/from Aiken and invest in infrastructure to highlight these points. 2) Develop maintenance plan along parkways and streets in Aiken for tree pruning, better visibility, lighting, and sidewalks where needed. | City of Aiken | The AMDC created a committee to support the Whiskey Road Corridor project by advising on economic development opportunties which will emerge from changes to traffic flow and access to property. | While this committee has not been active to date, there are activities taking place on this priority under other authorities.
Enhance South Boundary Avenue / gateway opportunities | 1) Explore strategies for highlighting South Boundary Avenue as a connector / gateway between Hitchcock Woods and Aiken's downtown core. | City of Aiken, Aiken Historical Museum, Hitchcock Woods Foundation, Chamber of Commerce, VisitAiken | The AMDC created a committee to support the Whiskey Road Corridor project by advising on economic development opportunties which will emerge from changes to traffic flow and access to property. | While this committee has not been active to date, there are activities taking place on this priority under other authorities.
2) Build into marketing and branding materials; explore connections to community assets such as the Aiken Historical Museum.
Chamber of Commerce Priorities
TASK | DESCRIPTION | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS | ASSESSMENT
Invest in minority and women’s business development | Design and implement programming to build bridges and share resources to maximize a more equitable, diverse and inclusive community for all. One focus would be improving access to tools, resources, funding and business opportunities for Minority and Women’s Business Enterprise (MWBE) businesses. Another focus would on improving access to education and workforce training resources and opportunities necessary to move people into higher paying jobs. | City of Aiken, Chamber of Commerce, AMDC | The Aiken Business Alliance Small Business Relief Grant Allocation Plan was established to provide financial capacity through the issuance of small grants and loans to support underserved businesses. This program is a partnership of the City of Aiken, the Aiken County NAACP, the Greater Aiken Chamber of Commerce and the Augusta Black Chamber of Commerce. By providing access to specialty training and capital the goal is to provide small businesses with the ability to grow and ultimately obtain financing through traditional means.
Build strong relationships with the region's top employers, local economic development organizations, and other key stakeholders | Ensure regular communication between local economic engines and the Aiken Chamber and other economic development entities. This will allow top employers to ensure that their needs (for an educated workforce, room for growth/expansion, etc.) are being met by the City/region, and in turn, allow the City to work on creative ways to leverage the presence of these key organizations into additional economic development opportunities for complimentary businesses/encourage "clustering" | Aiken Chamber, Local Employers (i.e. SRS, USC Aiken, Aiken Regional Medical Centers, etc.), Economic Development Partnership (EDP) | The Aiken Chamber’s First Friday Means Business program shares information with the broader community, and we plan to continue to invite speakers and subject matter that reflects the priorities of the AMDC and the City.
City Priorities
TASK | DESCRIPTION | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS | ASSESSMENT
Invest in existing parks, and create more small parks/green spaces close to residential areas that provide opportunities for recreation and socialization | Partner with residents and community organizations to offer more programming/amenities at existing parks, and ensure that those parks are well-advertised and accessible to as many Aiken residents as possible | City of Aiken, Neighborhood Associations/Other Community Organizations | MCL 12/21: Partner with over 75 community groups; an estimated 660 individual volunteers & 20 + residents who offer instructional programming. Advertising occurs through print and online media: social media (Facebook, Instagram); City Website; Aiken Standard (print and online); Park Bench publication (print and online); PeachJar (school flyer); e-Trac Emails; Flyers in PRT facilities; Billboards (Holiday campaign); Radio; Digital Marquees; and other various advertising partners. Engaged Community Residents and Organizations in participation in PRT Needs Assessment Survey and Master Planning process. Applied for park equity grants. | MCL 12/21: Continual growth of new partnerships as new businesses and groups are established in the community. New City website currently under construction-will work with IT Dept. to ensure that the new website is more user-friendly for promotion of PRT parks and programs. Continue search for grant funding relating to park equity.
| Assess current inventory of parks and open space by neighborhood; engage neighborhood associations, schools, and community groups to explore areas of need | City of Aiken, Neighborhood Associations/Other Community Organizations | MCL 12/21:The City of Aiken Parks, Recreation and Tourism Department has contracted with the Clemson University Department of Parks, Recreation and Tourism Management to develop an updated Master Plan to guide the future development and sustainability of park, land and recreational amenities in the City. Clemson's Dr. Bob Brookover has coordinated with PRT staff to develop a needs assessment survey, which was disseminated throughout the community for the month of October. Survey results will help information recommendations in the Plan. A public meeting is scheduled for Tuesday, November 9 at 5:30 at the Lessie B. Price Aiken Senior and Youth Center as a follow-up to the survey. | MCL 12/21: Data, feedback results, and recommendations will be presented to Aiken City Council and made available to the public at the conclusion of this process and will guide future investment and prioritization of the Department.
| Engage the Aiken Chamber's Aiken Young Professionals Group to lead discussions on strategies to attract young professionals and young families to Aiken; encourage them to survey their peers on changes they would like to see the City make going forward | Aiken Young Professionals Group/Aiken Chamber | MCL 12/21: Needs Assessment Survey, Focus Group and Public Input Meeting information were dispersed to Aiken Chamber. Chamber also encourages AYP to apply for nominations to hold seats on the City of Aiken Recreation Commission. | MCL 12/21: Encourage City PRT young professionals on staff to become involved in Chamber AYP group to further strengthen discussions.
Offer more programming/amenities at existing parks; ensure that parks are well-advertised to residents | Partner with local neighborhood associations and other community organizations to create more small parks/green spaces close to residential areas that provide opportunities for recreation and socialization | City of Aiken, Neighborhood Associations/Other Community Organizations | MCL 12/21: PRT partners with Crosland Park Neighborhood, Governor Aiken Park, and Toole Hill Neighborhood associations; engaged residents in planning of a playground replacement project at Crosland Park. Work closely with Senior Adult Community, with club meetings held regularly at Smith-Hazel and the Price Center. Needs Assessment Survey, Focus Group and Public Input Meeting information was dispersed to Neighborhood Associations and other community organizations (Recreation Commission, Arts Commission, Senior Commission, PRT Influencers (youth), Accommodations Tax Committee, Friends of Hopelands & Rye Patch, Friends of the Aiken Railroad Depot, Aiken Community Theatre, Aiken Performing Arts, Joye in Aiken, Aiken Symphony Orchestrat, Aiken Pickleball, Community Tennis Association, SRS Volleyball Club, AFC Futbol Club (soccer), American Legion Post 26, Athletic Directors of Public & Private schools; Aiken Downtown Development Association, UofSC Aiken, Farmers Market Committee, TRHOF Advisory Committee, Leadership Aiken County, etc...) | MCL 12/21: Data, feedback results, and recommendations will be presented to Aiken City Council and made available to the public at the conclusion of this process and will guide future investment and prioritization of the Department.
Explore new programming and entertainment options downtown | Engage the Aiken Chamber's Young Professionals group, along with local artists, musicians, and other stakeholders involved in the arts & entertainment fields to explore options for unique, regular programming and entertainment offerings downtown that will attract a wide audience, including non-Aiken residents. | Aiken Downtown Development Association, Aiken Music Festival | MCL 12/21: ADDA regularly receives requests/suggestions for new programming options downtown, and support with their limited staff capacity as much as possible. The City also partners with a wide range of community stakeholders for programming throughout the City. | MCL 12/21: City staff will share this task with ADDA and City Tourism staff for consideration.
Consider implementing protections for existing residents from gentrification | Explore options for implementing eviction protections, rent control, inclusionary zoning, and other policies and regulations designed to reduce gentrification pressures on existing residents | City of Aiken | n/a | MCL 12/21: City administration has requested that the Planning Commission study this topic and write a white paper summarizing their findings on the feasibility and appropriateness of these policy mechanisms for Council's consideration.
| Explore inclusionary zoning, tax credits, and other regulatory and incentive options for encouraging the private sector to invest in developing "missing middle" housing in Aiken, with Downtown being one area of focus | City of Aiken | n/a | MCL 12/21: City administration has requested that the Planning Commission study this topic and write a white paper summarizing their findings on the feasibility and appropriateness of these policy mechanisms for Council's consideration.
| Enforce existing zoning and building code property maintenance and upkeep regulations; write tickets and issue fines for properties not in compliance | City of Aiken | MCL 12/21: Zoning and Property Maintenance officials work hard to achieve compliance in the case of identified violations. They strive to achieve compliance by working with property owners rather than "throwing the book" at them. In many cases, when residents cannot afford a lawnmower or needed repairs to a building, assessing a fine only exacerbates the situation. Instead, our officials work to provide reasonable milestones for compliance and connect with community resources to mitigate the violation and prevent its recurrence. | MCL 12/21: None
Consider policies and regulations to encourage infill redevelopment | Initiate tax-foreclosure on properties that are both tax delinquent and vacant; work with local CDCs to find optimal solutions for redeveloping properties that have reverted to the City through this process | City of Aiken | MCL 12/21: City Finance staff oversee the process of property auctions for delinquent properties every year, in compliance with State law. Pursuant to Council directive, the City has engaged a real estate agent to help sell a docket of vacant and unutilized properties in its ownersip. | MCL 12/21: City staff can share this property list with the AMDC to determine if they would like to pursue marketing them to specific groups for specific uses, but City staff cannot engage in such undertakings.
| Explore options for additional regulations/enforcement measures to discourage property neglect and vacancy, including additional tax penalties for structures vacant longer than a certain time period (i.e. six months), similar to the "vacancy tax" recently adopted by the City of Los Angeles, CA | City of Aiken | MCL 12/21:The City of Aiken struggles to address the ills and complexities associated with "heir properties", as most cities do. To this end, staff remain abreast of best practices and network with other cities to monitor creative solutions that may be applied here. | MCL 12/21: Will continue to monitor relevant case law and legislation, as well as the efforts of peer cities, to identify solutions for the pervasive problems of neglect and vacancy.
Explore opportunities for shared parking downtown | Engage in a parking study of downtown. Determine when "peak parking hours" are for businesses downtown and explore opportunities for businesses with different parking needs to share parking areas. Analyze opportunities to create additional parking in areas where vacant land is unsuitable for new development; consider underground, elevated, and/or stacked parking options, to allow more cars to park in a smaller footprint. | City of Aiken, Aiken Downtown Development Association | MCL 12/21: The City of Aiken commissioned a downtown parking study in summer 2021 to be completed by a reputable traffic engineer. | MCL 12/21: Awaiting results.
Evaluate capacity of City Utilities to Expand Sewer Capacity in Support of Annexation Efforts | 1) Evaluate capacity of City Water and Wastewater utilities to support provision of public water and sewer as part of annexation strategies. | City of Aiken | MCL 12/21: In October 2021, interim Planning Director provided a comprehensive overview of strategic annexation to City Council. Efforts are actively underway to implement Council's annexation goals. An amended water/sewer annexation policy is slated for Council review at their 11/22/21 meeting. | MCL 12/21: Planning staff, in coordination with Engineering & Utility staff to assess utility capacity and priorities, will continue to actively work to support Council in their goals for strategic annexation.
2) Conduct outreach with residents to understand concerns related to annexation.
3) Confirm the business case for annexation
Work to improve City/County communication and collaboration on key issues | Establish a working group between Aiken City and Aiken County to regularly meet to communicate/collaborate on areas of mutual benefit/concern | City of Aiken, Aiken County, Aiken Chamber | MCL 12/21: City Manager Stuart Bedenbaugh meets regularly with Aiken County administration. | MCL 12/21: Continue regular manager meetings.
Partner with Hitchcock Woods Foundation to find areas of mutual benefit | Increasing utilization of Hitchcock Woods, and awareness of the park as a unique community amenity, would benefit both the Foundation and the City. A partnership between the Foundation, the City, the Chamber, and other stakeholders would allow the Foundation to leverage other resources to raise awareness of the park, improve programming options, and encourage visitation by both residents and visitors/tourists | City of Aiken, AMDC, Aiken Chamber, Hitchock Woods Foundation | TH: AMDC Program Manager should meet with Mayor and City Manager to create a plan to build upon recent agreements with the Hitchcock Woods Foundation and to expand them in the areas of increased awareness of the Woods, improved programming options, and increased visits by both residents and visitors/tourists. MCL 12/21: HW is already an established Tourism Partner. PRT is open to engaging with the Hitchcock Woods foundation and other mentioned stakeholders for increasing awareness. Tourism staff works closely with HW through award of Accomodations Tax Grant funds. Tourism staff engages with HW staff for arranging special tours, specifically to Public Relations (i.e. Travel Writers). Most recent set for 11/7. | MCL 12/21: Tourism is going through an updated Strategic Planning process that will further enhance engagement with community stakeholders. Education/training opportunities to help promote Aiken to both residetns and visitors is forthcoming in 2022.
Increase public awareness of Aiken as a "Community of Choice" | Engage in a targeted marketing campaign to ensure that visitors and people moving to the region for work are aware that Aiken is a "community of choice." Ensure that region's top employers have direct access to information on housing, schools, and amenities in the City of Aiken to use for recruiting and new hires. Update City/Chamber websites to direct potential residents to more information about schools, housing, and the high quality-of-life in Aiken | City of Aiken, Aiken Chamber | MCL 12/21: 1) The City of Aiken is actively pursuing increased staffing to assume such targeted marketing/communications efforts. 2) On 4/1/20, the Chamber of Commerce launched the"Welcome Neighbor" campaign, a high-tech targeted marketing campaign, in Columbia County, GA. | MCL 12/21: 1) Once staffed, the City can engage with Realtors and Planners/Developers along with Chamber, to develop a steering committee for this targeted marketing campaign. 2)Chamber will assess the effectiveness of the "Welcome Neighbor" campaign for possible expansion to the Beaufort and Lexington, SC markets.
Engage with local horse-enthusiast community stakeholders | Explore options for an Equine Heritage committee/task force of representatives from the equine community and other key stakeholders to establish goals for the equine industry in Aiken and the broader region, and guide equine-related economic development initiatives. Invite representatives from other communities that have successfully leveraged their equine resources for growth and economic development (Lexington, KY; Lexington, VA; Mill Spring, NC, etc.) to advise on best practices | Aiken Chamber, Aiken Steeplechase Association, Hitchcock Woods Foundation | TH: The Equine Heritage Committee and others in the industry should be encouraged to make recommendations to the AMDC and the Aiken City Council on productive ways to more fully realize benefits from the multiple events taking place which draw participants and spectators to our community. MCL 12/21: The City of Aiken has a City Council-appointed Equine Committee which could serve this end. | MCL 12/21: The Equine Committee has requested an audience with City Council to get direction on their purpose and mission and we can incorporate the Report recommendations in this discussion.
(who else should participate?)
Engage in a study to determine ways to leverage existing horse-industry-related assets in Aiken into a broader economic development strategy | It is recommended that the Equine Heritage committee/task Force engage industry experts to study the City/greater region for opportunities for a "destination" facility similar to the Kentucky Horse Park or Tryon International Equestrian Center that will both draw visitors/tourism to the region and provide an amenity for new and existing Aiken residents. This could be either at the new Steeplechase Site or at another location, if it is better-suited. | City of Aiken, Aiken Chamber | TH: With recent developments at Bruce's Field and the construction of a new Steeplechase site with many other amenities, it does not appear that a Horse Park would be successful, or, at worst, might be successful at the expense of existing businesses. In that light, other options should be explored with the Equine Heritage Committee and others to more fully leverage the investments and attractiveness of businesses in this field already operating within our community. MCL 12/21: The goal of this task has been accomplished by the work of two separate local horse groups: the Aiken Steeplechase and Aiken Horse Park (Bruce's Field). Both are investing millions of dollars, including hundreds of thousands from the City, to update their facilites to expand Aiken's brand as a premier equestrian destination for a wide array of horsing disciplines. | No study needed.
Develop neighborhood services and housing | Assess development potential of former Sav-A-Lot site for grocery and neighborhood retail with housing. | City of Aiken, AMDC, Neighborhood Associations | MCL 12/21: This site has been redeveloped, and currently houses a thriving restaurant/bar/pool hall. | MCL 12/21: City Economic Development staff will continue their ongoing work of supporting developers in strategically investing in our City in ways that are mutually benefical for all.
(What is new objective here?)
Strengthen connection along Route 1 to I-20 | 1) Assess connecting Generations Park via a multi-modal trail. | City of Aiken, AMDC | MCL 12/21: As a part of the annexation presentation to City Council, Interim Planning Director Marya Moultrie shared the possibility of a multi-modal trail. Initial conversations have been had with Norfolk Southern about having the abandoned railway deeded to the City for use as a trail. | MCL 12/21: City staff will continue discussions with critical landowners along route.
2) Identify potential sites along Route 1 for development.
Enhance South Boundary Avenue / gateway opportunities | 1) Explore strategies for highlighting South Boundary Avenue as a connector / gateway between Hitchcock Woods and Aiken's downtown core. | City of Aiken, Aiken Historical Museum, Hitchcock Woods Foundation, Chamber of Commerce, VisitAiken | MCL 12/21: 1. TBD. 2. Public Services has maintenance plan in place.
2) Build into marketing and branding materials; explore connections to community assets such as the Aiken Historical Museum.
1) Confirm key entrance and exits to/from Aiken and invest in infrastructure to highlight these points.
2) Develop maintenance plan along parkways and streets in Aiken for tree pruning, better visibility, lighting, and sidewalks where needed.
Boost pedestrian and multi-modal accessibility | Identify key pedestrian crossings (existing and needed) and develop improvement plan for crosswalks with striping, lighting and warning lights. | City of Aiken, Downtown Development Association, Neighborhood Associations | The AMDC created a committee to support the Whiskey Road Corridor project by advising on economic development opportunties which will emerge from changes to traffic flow and access to property. | This committee has not been active to date.
2) Create bike and walking promenades and paths for greater connections in neighborhoods to parks, schools, community centers, and shopping.
Assess grant programs as incentives for development | Assess using grant programs for rebuilding / refreshing facades, installation of grease traps, green infrastructure, and district-scale stormwater management solutions. | City of Aiken | MCL 12/21: The City of Aiken offers a Façade Grant. | MCL 12/21: City will pursue funding as grant opportunities are available and feasible.
Boost pedestrian and multi-modal accessibility | Identify key pedestrian crossings (existing and needed) and develop improvement plan for crosswalks with striping, lighting and warning lights. | City of Aiken, Downtown Development Association, Neighborhood Associations | MCL 12/21: Because the vast majority of roadways within the City limits are SCDOT roads, the City is very limited in what we can for pedestrian crossings, bike and walk paths, etc. The City works regularly with SCDOT to identify and mitigate hazards within the confines of state law and SCDOT standards. The City has pursued grant funding on numerous occasions to fund enhancements to our pedestrian infrastructure. | MCL 12/21: The City will maintain its positive working relationship wth DOT to ensure timely response in addressing hazards, and will continue to pursue grant funding to expand/improve multi-modal infrastructure where feasible/appropriate and consistent with City Council directives.
2) Create bike and walking promenades and paths for greater connections in neighborhoods to parks, schools, community centers, and shopping.
Invest in multi-modal transportation infrastructure linking homes, job centers, amenities, and retail/services | Although Aiken may not have the population size or density for a robust fixed public transportation system, there are many lower-cost, smaller-scale alternatives that the City should explore for providing better linkages between homes, job centers, and retail and services. Increasing bicycle and pedestrian infrastructure, particularly in growth centers, would both better serve existing residents, and offer alternative modes of transportation that are increasingly demanded by Millennials and Gen Z-ers. | City of Aiken, Aiken County Public Transit | MCL 12/21: Because the vast majority of roadways within the City limits are SCDOT roads, the City is very limited in what we can for pedestrian crossings, bike and walk paths, etc. The City works regularly with SCDOT to identify and mitigate hazards within the confines of state law and SCDOT standards. The City has pursued grant funding on numerous occasions to fund enhancements to our pedestrian infrastructure. | MCL 12/21: The City of Aiken Planning and CPST staff will continue to assess opportunities for enhanced multi-modal infrastructure and will pursue funding where available and as feasible/appropriate and consistent with City Council directives.
Education-Related Priorities
TASK | TASK | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS
Provide workforce development opportunities for Aiken residents | Strengthen partnerships between USC Aiken, Aiken Technical College, major employers, and the local community to ensure that Aiken residents have the opportunity to gain skills and abilities that match what the region's top employers are looking for. Implement new and/or strengthen existing programs that provide a smooth "pipeline" from USC Aiken, Aiken Technical, and local high schools to jobs in the region through co-op, internship, and apprenticeship programs | Aiken Chamber, USC Aiken, Aiken Technical, Aiken Public Schools | The AMDC has hired a Program Manager to work with the City in developing a plan to initiate conversations with the various education sectors in our community to pursue opportunities of mutual interest. | The Program Manager has begun conversations with the Mayor about a path forward and will be pursuing meetings with other key players to organize a meeting.
Invest in K-12 education | Work with Aiken Public Schools to launch a public campaign on social media and other platforms to correct misperceptions about public school quality in Aiken; ensure that this information is available to local businesses, particularly real estate professionals. This should include search engine optimization, to ensure correct information is readily available to residents and prospective residents doing web searches about Aiken school quality. | USCA, ATC, Aiken Public Schools, Aiken Chamber | The AMDC has hired a Program Manager to work with the City in developing a plan to initiate conversations with the various education sectors in our community to pursue opportunities of mutual interest. | The Program Manager will contact the Chancellor at USC Aiken to make inquiries about the viability of this recommendation.
| Partner public schools with local institutions of higher learning (USC Aiken, Aiken Technical College) to offer apprenticeships and co-ops for high-school students, aligned with opportunities in R&D, advanced manufacturing, and software / IT. | Aiken Public Schools, USC Aiken, Aiken Technical College
Work with USC Aiken to provide students with opportunities in the local equine veterinary industry | USC Aiken offers a pre-veterinary science pre-professional program. This is another opportunity for the City to partner with the University to link students and professionals in the veterinary field with an interest in the equine industry to Aiken’s existing horse-enthusiast community, and increase resident retention | City of Aiken; USC Aiken; Aiken Steeplechase Association | The AMDC has hired a Program Manager to work with the City in developing a plan to initiate conversations with the various education sectors in our community to pursue opportunities of mutual interest.
Provide workforce development opportunities for Aiken residents | Strengthen partnerships between USC Aiken, Aiken Technical College, major employers, and the local community to ensure that Aiken residents have the opportunity to gain skills and abilities that match what the region's top employers are looking for. Implement new and/or strengthen existing programs that provide a smooth "pipeline" from USC Aiken, Aiken Technical, and local high schools to jobs in the region through co-op, internship, and apprenticeship programs | Aiken Chamber, USC Aiken, Aiken Technical, Aiken Public Schools | The AMDC Chair will participate in upcoming meetings between the Mayor and the leaders in these sectors to pursue these objectives.
| Establish a small-business incubator in Downtown and/or at USC Aiken/the proposed Innovation District to nurture local small businesses and encourage entrepreneurship. Encourage existing successful Aiken-based small- and medium-sized businesses to "mentor" start-ups/new businesses | USCA, Aiken Chamber, Aiken Chamber, Aiken Downtown Development Association, other local employers, SCORE, Small Business Development Center (SBDC) | The AMDC plans to invite the Chancellor at USC Aiken to address the group in the near future, and this will be a topic for discussion with him in planning for that meeting and, as appropriate, during that interaction.
Healthcare-Related Issues
TASK | DESCRIPTION | RESPONSIBLE PARTIES | PROGRESS | NEXT STEPS
Invest in healthcare services | Work with local providers to ensure that existing facilities and services are connected with those who need them through targeted outreach, marketing, and community engagement | Aiken Chamber, City of Aiken, Local Healthcare Providers | The AMDC has hired a Program Manager to work with the City in developing a plan to initiate conversations with the various education sectors in our community to pursue opportunities of mutual interest. | The Program Manager has begun conversations with the Mayor about a path forward and will be pursuing meetings with other key players to organize a meeting.
| Consider the formation of a health care foundation to support strategies to target and retain more specialists to Aiken, particularly in geriatrics, memory care, and other specialties that serve an aging population | City of Aiken, Aiken Chamber, Local Healthcare Providers | The AMDC has hired a Program Manager to work with the City in developing a plan to initiate conversations with the various education sectors in our community to pursue opportunities of mutual interest. | The Program Manager has begun conversations with the Mayor about a path forward and will be pursuing meetings with other key players to organize a meeting.
| Partner with local hospitals and care facilities and evaluate incentives to support expansion of health care services, to provide more services locally, so residents don't have to travel outside the City/County for treatment | Aiken Chamber, City of Aiken, Local Healthcare Providers | The AMDC has hired a Program Manager to work with the City in developing a plan to initiate conversations with the various education sectors in our community to pursue opportunities of mutual interest.
| Partner with local care facilities and industry groups to explore ways to provide differing levels of care to aging residents, from independent living through full-time nursing care, and in-home health treatment options | Aiken Chamber. City of Aiken, Local Healthcare Providers | The AMDC has hired a Program Manager to work with the City in developing a plan to initiate conversations with the various education sectors in our community to pursue opportunities of mutual interest.

## AMDC Goals
AMDC Goals and Committee Assignments
Goal/Committee # | Goal Title | Goal Statement
1 | Aiken Innovation and Impact District | The AMDC will spearhead the development of an Innovation and Impact district to capitalize upon imminent investments being made on and near the campus of the university of South Carolina Aiken such as the Advanced Manufacturing Center and the South Carolina National Guard DreampPort. These projects are expected to be in operation within the next 2-3 years, and it is imperative that efforts to secure land, establish partnerships, anticipate policy changes necessary for this venture's success, and planning for appropriate amenities to support a living/working environment to attract and retain a world-class collection of businesses, investors and employees.
2 | Whiskey Road Corridor/Development Ramifications of Transportation Improvements | The AMDC will support efforts by the City and County to implement existing plans for significant improvements to traffic flow, safety, and increased economic development.
3 | Targeted Residential and Business Development | The AMDC will create new opportunities for commercial and residential development through partnerships and existing groups, as well as new investors, to increase the quality and density of those living and working within the City of Aiken.
4 | Making Aiken More "Business Friendly"
5 | Marketing Aiken as a Good Community for Investment
Committee Assignments:
G-1 Innovation Center
G-2 Supporting the Whiskey Rd. Corridor Project/Development Ramifications of Transportation Improvements
G-3 Targeted Residential and Business Development
G-4 Making Aiken More "Business Friendly"
G-5 Marketing Aiken as a Good Community for Investment